## Product Backlog
Online Merchandising Store
Theme | ID | User Story | Acceptance Criteria | Comments | Sprint | Status | Points | Days
Admin | ADM1 | As an Admin I want to login to admin dashboard So I can manage all the necessary stuff. | a) View all the admin Dashboard |  | 1 |  | 10 | 3
| ADM2 | As a Admin I want to view the change password page So I can change or update my password as required. | a) To Perform these activities view the change password page |  | 1 |  | 10 | 2
| ADM3 | As a Admin I want to manage users So I can add, delete and update them. | a) To Perform CRUD on Users List |  | 1 |  | 10 | 2
| ADM4 | As a Admin I want to insert product according So I can show the new product. | a) To insert new product |  | 2 |  | 30 | 6
| ADM5 | As a Admin I want to manage products So I can update or delete the existing product details. | a) To Perform CRUD on existing products |  | 2 |  | 30 | 6
| ADM6 | As a Admin I want to view the orders page So I can see all the orders and update their status | a) To see the list the orders |  | 3 |  | 20 | 4
| Total for theme 'Admin' |  |  | 110.0 points / 23 days
User | USR1 | As a User I want to register myself to the system So I can use it. | a) Fill the registeration form |  | 1 |  | 10 | 2
| USR2 | As a User I want to view my details So I can add or update it. | a) View profile details |  | 1 |  | 10 | 2
| USR3 | As a User I want to change my password So I can keep my account secure | a) Go to change password/forget password page |  | 1 |  | 10 | 2
| USR4 | As a User I want to add my Shipping address So I can get the percel in my concern place | a) Fill the details of Shipping Address |  | 1 |  | 10 | 2
| USR5 | As a User I want the payment methods So I can pay for the product accordingly. | a) Go to the payement page and fill all the required details |  | 2 |  | 10 | 2
| USR6 | As a User I want to look for different categories of products So I can buy according to my choice | a) View home page and choose category as per required |  | 2 |  | 30 | 6
| USR7 | As a User I want to see the product details So I can know the product and add them to my cart | a) Click on any specific product and view all the details |  | 2 |  | 15 | 3
| USR8 | As a User I want to order my product So I can buy them | a) Go to My cart and click proceed to purchage or confirm your order |  | 2 |  | 10 | 2
| USR9 | As a User I want to to track my order So I can know the status of it | a) Track the product by using tracking ID |  | 3 |  | 10 | 2
| USR10 | As a User I want to to see the review and add my review So I can analyze the product before buying it | a) View the product reviews |  | 3 |  | 10 | 2
| USR11 | As a User I want to to able to find a contact information of the site So I can contact them if I require. | a) View the contact details at the bottom of the page and at contact us page |  | 3 |  | 10 | 2
| Total for theme 'User' |  |  | 135.0 points / 27 days